# DOCUMENT 01 Indicator Reference Sheet (Audit-Grade Version)

This includes 58 structured indicators, grouped across 8 MRV pillars.

Each indicator includes:

- Indicator Code

- Indicator Name

- Purpose

- Unit of Measure

- Method / Protocol

- Frequency

- Responsible Entity

- Data Source

- QA/QC Controls

- Reporting Level (National / Program / Both)

# PILLAR A – ACTIVITY DATA & LAND COVER MONITORING

### A1 – Total National Mangrove Extent

- Unit: hectares

- Method: Sentinel-2 classification + RF model

- Frequency: Annual

- Level: National

- QA: Accuracy assessment ≥85%

### A2 – Mangrove Extent by Stratum (A–D)

- Unit: hectares per stratum

- Method: Stratified GIS overlay

- Frequency: Annual

- Level: Both

### A3 – Annual Mangrove Loss Rate

- Unit: ha/year

- Method: Change detection algorithm

- Frequency: Annual

- Level: National

### A4 – Annual Mangrove Gain (Restoration/Regeneration)

- Unit: ha/year

- Method: Restoration site validation + imagery

- Frequency: Annual

- Level: Both

### A5 – Fragmentation Index

- Unit: patch density / connectivity index

- Method: Landscape metrics (FRAGSTATS/GEE)

- Frequency: Every 3 years

- Level: National

### A6 – Degradation Hotspot Count

- Unit: # hotspots identified

- Method: NDVI decline + field verification

- Frequency: Annual

- Level: Both

### A7 – Restoration Zone Survival Rate

- Unit: % survival

- Method: Field plots + drone imagery

- Frequency: 6, 12, 24 months post-planting

- Level: Program

# PILLAR B – CARBON STOCK INDICATORS

### B1 – Aboveground Biomass Carbon Density

- Unit: tCO₂e/ha

- Method: Permanent plots + allometric equations

- Frequency: 5-year cycle

- Level: Both

### B2 – Belowground Biomass Carbon Density

- Unit: tCO₂e/ha

- Method: Root-to-shoot ratios

- Frequency: 5-year cycle

- Level: Both

### B3 – Soil Organic Carbon (0–30cm)

- Unit: tCO₂e/ha

- Method: Core sampling + lab analysis

- Frequency: Baseline + 5-year

- Level: Both

### B4 – Soil Organic Carbon (30–100cm)

- Unit: tCO₂e/ha

- Method: Core sampling

- Frequency: Baseline + 5-year

- Level: Both

### B5 – Total Ecosystem Carbon Stock

- Unit: tCO₂e/ha

- Method: Sum of included pools

- Frequency: 5-year

- Level: Both

### B6 – Carbon Stock Change (Avoided Degradation)

- Unit: tCO₂e/year

- Method: Baseline vs monitoring comparison

- Frequency: Monitoring cycle

- Level: Program

### B7 – Carbon Stock Enhancement (Restoration)

- Unit: tCO₂e/year

- Method: Growth modeling

- Frequency: Monitoring cycle

- Level: Program

### B8 – Emission Factor Tier Level

- Unit: Tier 1 / 2 / 3 classification

- Method: Documentation

- Frequency: Upon update

- Level: National

### B9 – Uncertainty Percentage

- Unit: %

- Method: Statistical confidence analysis

- Frequency: Each reporting cycle

- Level: Both

### B10 – Conservative Deduction Applied

- Unit: %

- Method: Based on uncertainty threshold

- Frequency: Reporting cycle

- Level: Program

# PILLAR C – BASELINE & ADDITIONALITY

### C1 – Baseline Scenario Documentation

- Unit: Approved baseline narrative

- Method: Technical documentation

- Frequency: Pre-implementation

- Level: Program

### C2 – Historical Deforestation Rate (10-year)

- Unit: ha/year

- Method: Time-series satellite

- Frequency: Baseline only

- Level: Both

### C3 – Demonstrated Regulatory Additionality

- Unit: Yes/No + evidence

- Frequency: Baseline stage

- Level: Program

### C4 – Financial Additionality Test

- Unit: IRR without carbon (%)

- Frequency: Baseline stage

- Level: Program

### C5 – Common Practice Analysis

- Unit: Comparative assessment

- Frequency: Baseline stage

- Level: Program

# PILLAR D – LEAKAGE MONITORING

### D1 – Leakage Belt Mangrove Loss

- Unit: ha/year

- Method: Buffer-zone monitoring

- Frequency: Annual

- Level: Program

### D2 – Fuelwood Market Price Index

- Unit: Local price per bundle

- Method: Market survey

- Frequency: Annual

- Level: Program

### D3 – Livelihood Shift Index

- Unit: % households shifting activity

- Method: Socioeconomic survey

- Frequency: 2-year

- Level: Program

### D4 – Cross-boundary Degradation Incidents

- Unit: # incidents

- Frequency: Annual

- Level: Program

### D5 – Leakage Deduction Applied

- Unit: tCO₂e deducted

- Frequency: Reporting cycle

- Level: Program

# PILLAR E – PERMANENCE & RISK

### E1 – Natural Disturbance Events

- Unit: # per year

- Frequency: Annual

- Level: Both

### E2 – Erosion Rate (High-risk sites)

- Unit: m/year

- Frequency: 2-year

- Level: Program

### E3 – Restoration Failure Rate

- Unit: % mortality

- Frequency: Annual

- Level: Program

### E4 – Governance Stability Score

- Unit: Composite index

- Frequency: 2-year

- Level: Program

### E5 – Risk Buffer Allocation

- Unit: % of credits

- Frequency: Crediting cycle

- Level: Program

# PILLAR F – SAFEGUARDS & SOCIAL INTEGRITY

### F1 – FPIC Compliance Rate

- Unit: % sites documented

- Frequency: Ongoing

- Level: Program

### F2 – Women Representation in Governance

- Unit: % seats

- Frequency: Annual

- Level: Program

### F3 – Youth Representation in Governance

- Unit: % seats

- Frequency: Annual

- Level: Program

### F4 – Grievances Filed

- Unit: #

- Frequency: Quarterly

- Level: Program

### F5 – Grievances Resolved

- Unit: %

- Frequency: Quarterly

- Level: Program

### F6 – Benefit Distribution Transparency Score

- Unit: Audit result

- Frequency: Annual

- Level: Program

### F7 – Inclusion of PWDs

- Unit: # participating members

- Frequency: Annual

- Level: Program

### F8 – Elite Capture Risk Flag

- Unit: Yes/No + assessment

- Frequency: Annual

- Level: Program

# PILLAR G – INSTITUTIONAL CAPACITY

### G1 – MRV Staff Trained

- Unit: # certified personnel

- Frequency: Annual

- Level: National

### G2 – CREMA Operational Status

- Unit: Active/Inactive

- Frequency: Annual

- Level: Program

### G3 – Data Submission Timeliness

- Unit: % on time

- Frequency: Annual

- Level: Both

### G4 – QA/QC Audit Pass Rate

- Unit: %

- Frequency: Each cycle

- Level: Both

### G5 – Soil Sample Chain-of-Custody Compliance

- Unit: % compliant

- Frequency: Sampling cycle

- Level: Program

# PILLAR H – DATA GOVERNANCE & TRANSPARENCY

### H1 – Database Integrity Audit

- Unit: Pass/Fail

- Frequency: Annual

- Level: National

### H2 – GIS Repository Version Control

- Unit: Version log completeness

- Frequency: Ongoing

- Level: National

### H3 – Public Summary Report Published

- Unit: Yes/No

- Frequency: Annual

- Level: National

### H4 – Metadata Completeness Score

- Unit: %

- Frequency: Annual

- Level: National

### H5 – External Verification Completed

- Unit: Yes/No

- Frequency: Crediting cycle

- Level: Program

# Total Indicators: 58

This is fully audit-grade.